# Complete Research Standard Operating Procedure

Agreement Is Not Truth: from topic to submission

22 October 2026

# How to read this SOP

Each phase gives the objective, prerequisites, actions, commands, outputs, quality checks, common errors, troubleshooting and the completion criterion. Status as of 22 October 2026: phases 1 to 11 and 16 to 17 are done in the repository (11 on the simulated model); phases 12 to 15 and 18 to 23 need GPU runs or author judgment.

# Phase 1. Topic validation

- Objective: confirm the topic is relevant, feasible and new enough.

- Prerequisites: team literature sheet (20 papers).

- Actions: group limitations; score impact, feasibility, novelty; choose G1 (consistent errors).

- Outputs: “Limitation Groups” and “Experiment Options” tabs; proposal document.

- Quality checks: at least 10 papers share the gap; the experiment fits free or low cost GPUs.

- Common errors: choosing the most cited gap without checking it is already solved.

- Troubleshooting: run a targeted search for the exact gap before committing.

- Completion: gap and option recorded; novelty search done (found Tan et al. 2025 and narrowed to the black box, training free angle).

# Phase 2. Literature review

- Objective: know what exists, what works and what is missing.

- Actions: read the 20 papers; search arXiv, ACL Anthology, Semantic Scholar; extract method, data, results, limits.

- Outputs: docs/LITERATURE_REVIEW.docx; team sheet.

- Quality checks: every claim in the paper’s related work traces to a read source.

- Common errors: citing from abstracts only; trusting secondary summaries.

- Completion: comparison table and gap statement written.

# Phase 3. Research gap identification

- Objective: a gap that is real, not speculative.

- Actions: compare the closest works on access, training, target error type, sycophancy control.

- Outputs: gap section of the review; Table 7 of the review.

- Completion: gap stated in one sentence and defended against the three closest papers.

# Phase 4. Research question formulation

- Objective: testable questions with fixed success criteria.

- Outputs: H1 to H4 in docs/EXPERIMENTAL_PROTOCOL.md.

- Quality checks: each hypothesis has a numeric criterion and a failure condition.

- Completion: criteria fixed before the pilot.

# Phase 5. Dataset selection

- Objective: data that produce consistent errors and match prior work.

- Actions: choose TruthfulQA, TriviaQA, SciQ; pin revisions; check licenses.

- Outputs: docs/DATASET_DOCUMENTATION.md; data.py.

- Common errors: unpinned dataset versions; license misuse (SciQ is non commercial).

- Completion: revisions pinned, licenses recorded.

# Phase 6. Methodology design

- Objective: a design where the comparison is fair and the conclusion follows from the data.

- Actions: paired design; matched classes; same samples for all methods; doubt control; ablations.

- Outputs: protocol sections 4 to 7; paper Method section.

- Completion: every design choice has a reason written next to it.

# Phase 7. Experimental protocol finalisation

- Objective: freeze settings before results exist.

- Actions: finalise configs; record the change log.

- Commands: git add configs docs/EXPERIMENTAL_PROTOCOL.md && git commit -m "Freeze protocol".

- Completion: protocol committed.

# Phase 8. Codebase development

- Objective: a reproducible pipeline from questions to paper.

- Outputs: src/pressure_probe/, configs, notebooks.

- Quality checks: one responsibility per file; all prompts in one module; no hardcoded paths or keys.

- Completion: every stage runs on the simulated backend.

# Phase 9. Unit testing

- Commands: python -m pytest -q tests/test_metrics.py tests/test_scoring.py tests/test_text_split_config.py.

- Quality checks: metric code compared with scikit-learn and with bootstrap; Holm against known values.

- Completion: all unit tests pass (see docs/TEST_REPORT.md).

# Phase 10. Integration testing

- Commands: python -m pytest -q tests/test_pipeline_mock.py tests/test_report.py.

- Quality checks: resume after interruption; idempotent reruns; every result token resolves; PDF within 10 pages; Word file has yellow highlights.

- Completion: all pass.

# Phase 11. Smoke testing (Colab, Mode A)

- Objective: prove every stage works on a real GPU.

- Actions: run notebooks/smoke_test.ipynb.

- Outputs: results/smoke/ and a throwaway PDF.

- Common errors: CPU runtime; missing HF_TOKEN; vLLM not supported (falls back automatically).

- Completion: all cells finish; validation report shows a page count.

# Phase 12. Pilot experiment (Mode B)

- Objective: check the CW count, the pressure signal and runtime.

- Actions: run notebooks/pilot_experiment.ipynb.

- Quality checks: CW at least 15 per model; a pressure score above 0.6 for one model; stage times in timings.

- Outcome (27 October 2026): CW 62 and 33; CPS failed (0.53, 0.40) while the doubt flip rate reached 0.69 and 0.65, so protocol version 2 made DFR the main score before the full run.

- Troubleshooting: low CW: raise TruthfulQA share; no signal: stop and review prompts before spending on the full run.

- Completion: go or no go decision written in the protocol change log.

# Phase 13. Full experiments (Mode C)

- Actions: size configs/full.yaml from the pilot; run notebooks/full_experiment.ipynb stage by stage.

- Commands: python -m pressure_probe.cli run --config configs/full.yaml.

- Common errors: session limits (rerun the cell; work resumes); out of memory (lower batch_size).

- Completion: results/full/summary.json exists with mode: full.

# Phase 14. Ablation studies

- Objective: isolate the contribution of the number of doubt prompts, the counterclaim, the subtraction (CPS) and the combination with X.

- Actions: none extra; ablations are computed in evaluate from stored replies (random alternative is collected in probe).

- Completion: ablation table filled in the paper.

# Phase 15. Statistical analysis

- Actions: python -m pressure_probe.cli stage evaluate --config configs/full.yaml.

- Quality checks: intervals present for every AUROC; Holm adjusted p values; hypothesis verdicts.

- Common errors: reading overlapping intervals as “no difference”; use the paired test.

- Completion: summary.json complete.

# Phase 16. Figure and table generation

- Commands: part of report.

- Quality checks: fonts at least 6 pt in print; colours pass the palette check; every mark labelled.

- Completion: figures in paper/generated/.

# Phase 17. Automated manuscript updating

- Commands: python -m pressure_probe.cli report --config configs/full.yaml.

- Outputs: paper/main.tex, paper/paper.pdf, paper/paper.docx, paper/validation_report.json, dist/full_package.zip.

- Quality checks: unresolved_tokens empty; todo_marks equals the author review boxes and author fields left.

- Completion: only author written parts remain yellow.

# Phase 18. Scientific interpretation

- Objective: explain the results without overclaiming.

- Actions: replace the three review boxes in paper/main.template.tex; use examples from scores.csv and the examples table.

- Quality checks: every causal statement is marked as interpretation; no new numbers typed by hand.

- Completion: all authors agree with the discussion.

# Phase 19. Citation verification

- Actions: resolve the six Check rows in docs/CITATION_VERIFICATION_REPORT.md; rerun the related work search.

- Completion: no unverified entry remains.

# Phase 20. Manuscript editing

- Commands: python tools/check_writing.py paper/main.template.tex.

- Quality checks: zero listed terms and dashes; hyphens only in names and identifiers; sentences under 25 words where possible.

- Completion: checker passes and two authors have read the paper aloud once.

# Phase 21. IEEE formatting validation

- Quality checks: at most 10 pages including references; IEEEtran conference class; no Type 3 fonts; figures readable; PDF eXpress if the portal asks.

- Completion: ready_to_submit: true in the validation report.

# Phase 22. Independent peer review

- Actions: a colleague outside the project reads the PDF with docs/REVIEWER_REPORT.md as a checklist; fix what they find.

- Completion: all serious points resolved or acknowledged in Limitations.

# Phase 23. Final submission preparation

- Actions: follow docs/SUBMISSION_CHECKLIST.md; confirm the S25 track deadline; all authors approve.

- Completion: submitted by hand through CyberChair.